## Sheet1
# | Task Name | What Happens | Output | Hours | Stage | Phase
1 | Stakeholder & Planning Setup | Identify stakeholders, define session plan, confirm scope areas | Stakeholder map + plan | 4 | Requirements gathering/Process Mapping/Solution Output | Phase 1
2 | Application & Lifecycle Workshop | Full-day session covering application flow end-to-end (entry → submission → review → decision) including edge cases | Core lifecycle definition | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
3 | Assessment & Decision Workshop | Scoring models, assessor roles, moderation, approvals, exceptions | Assessment model | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
4 | Committee Variation Workshop | How different committees operate, key differences and constraints | Variation matrix | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
5 | Funding & Scholarship Workshop | Funding models, allocation, adjustments, lifecycle | Funding structure defined | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
6 | Data & Edge Case Workshop | Required data, dependencies, unusual scenarios, failures | Data requirements + edge cases | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
7 | Integration & Reporting Workshop | External systems, data flow, reporting needs (decision-led) | Integration + reporting definition | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
8 | Engagement & Non-Application Workshop | Events, outreach, additional interactions | Engagement flows | 5 | Requirements gathering/Process Mapping/Solution Output | Phase 1
9 | Follow-up / Gap Session | Revisit unclear areas, challenge assumptions, close gaps | Gap log resolved | 5 | Requirements gathering/Process Mapping/Solution Output | Phase 1
10 | Process Mapping (Core) | Convert workshops into structured process maps (applications, assessment, funding) | Process maps v1 | 10 | Requirements gathering/Process Mapping/Solution Output | Phase 1
11 | Variation & Edge Case Mapping | Overlay variations and edge cases into core flows | Unified process model | 6 | Requirements gathering/Process Mapping/Solution Output | Phase 1
12 | Validation Session | Walkthrough with stakeholders, confirm accuracy, capture feedback | Feedback notes | 4 | Requirements gathering/Process Mapping/Solution Output | Phase 1
13 | Process Refinement | Apply feedback, finalise flows | Final process maps | 6 | Requirements gathering/Process Mapping/Solution Output | Phase 1
14 | System Translation | Convert processes into system design (entities, lifecycle, roles) | System design model | 8 | Requirements gathering/Process Mapping/Solution Output | Phase 1
15 | Data Definition | Define fields, ownership, validation rules | Data model + field list | 8 | Requirements gathering/Process Mapping/Solution Output | Phase 1
16 | Final Design Walkthrough | End-to-end review of system design | Final validation | 4 | Requirements gathering/Process Mapping/Solution Output | Phase 1
17 | Design Lock | Confirm sign-off and readiness for build | Approved design | 2 | Requirements gathering/Process Mapping/Solution Output | Phase 1
18 | Zoho Org Setup | Create org, configure company settings, branding, timezone, currency | Environment ready | 4 | Implementation | Phase 2
19 | Email & Domain Setup | Configure email routing, sender authentication, domain settings | Email working | 3 | Implementation | Phase 2
20 | App Enablement | Enable CRM, Forms, Analytics, Flow and required services | Apps active | 3 | Implementation | Phase 2
21 | Global Settings Review | Review and clean default system settings | Clean system base | 2 | Implementation | Phase 2
22 | Role Hierarchy Setup | Build hierarchy for central, committees, assessors | Role structure | 6 | Implementation | Phase 2
23 | Profile Setup | Configure module, field, action permissions | Profiles ready | 6 | Implementation | Phase 2
24 | Permission Rules | Configure sharing rules and visibility | Data access model | 8 | Implementation | Phase 2
25 | Initial User Creation | Create admin and key users | Users active | 4 | Implementation | Phase 2
26 | Module Creation – Individuals | Create core individual record structure | Module live | 4 | Implementation | Phase 2
27 | Module Creation – Applications | Create application structure | Module live | 4 | Implementation | Phase 2
28 | Module Creation – Committees | Create governance structure | Module live | 3 | Implementation | Phase 2
29 | Module Creation – Assessments | Create review structure | Module live | 4 | Implementation | Phase 2
30 | Module Creation – Funding | Create scholarship structure | Module live | 4 | Implementation | Phase 2
31 | Module Creation – Engagement | Create events/activity tracking | Module live | 5 | Implementation | Phase 2
32 | Module Creation – Organisations | Create partner/school structure | Module live | 5 | Implementation | Phase 2
33 | Field Creation – Individuals (Core) | Create demographic and contact fields | Fields live | 6 | Implementation | Phase 2
34 | Field Creation – Individuals (Extended) | Add lifecycle, status and classification fields | Fields live | 6 | Implementation | Phase 2
35 | Field Creation – Applications (Core) | Create application stage, type, source fields | Fields live | 7 | Implementation | Phase 2
36 | Field Creation – Applications (Decision) | Create decision and outcome fields | Fields live | 7 | Implementation | Phase 2
37 | Field Creation – Assessments | Create scoring and review fields | Fields live | 10 | Implementation | Phase 2
38 | Field Creation – Funding | Create funding allocation and tracking fields | Fields live | 10 | Implementation | Phase 2
39 | Field Creation – Committees | Create governance and membership fields | Fields live | 8 | Implementation | Phase 2
40 | Field Creation – Engagement | Create event/activity fields | Fields live | 8 | Implementation | Phase 2
41 | Lookup Relationships | Configure relationships between modules | Linked data | 12 | Implementation | Phase 2
42 | Related Lists Setup | Configure related record visibility | Navigation ready | 6 | Implementation | Phase 2
43 | Layout Build – Individuals | Build layouts and sections | Layout ready | 5 | Implementation | Phase 2
44 | Layout Build – Applications | Build layouts and sections | Layout ready | 6 | Implementation | Phase 2
45 | Layout Build – Assessments | Build layouts and sections | Layout ready | 4 | Implementation | Phase 2
46 | Layout Build – Funding | Build layouts and sections | Layout ready | 4 | Implementation | Phase 2
47 | Layout Build – Committees | Build layouts and sections | Layout ready | 4 | Implementation | Phase 2
48 | Validation Rules Setup | Configure required fields and rules | Validation active | 10 | Implementation | Phase 2
49 | Duplicate Rules Setup | Configure duplicate detection | Clean data rules | 6 | Implementation | Phase 2
50 | Lifecycle Stage Setup | Configure statuses and transitions | Lifecycle active | 10 | Implementation | Phase 2
51 | Workflow – Application | Build lifecycle automation | Workflow active | 14 | Implementation | Phase 2
52 | Workflow – Assessment | Build review automation | Workflow active | 10 | Implementation | Phase 2
53 | Workflow – Decision | Build decision automation | Workflow active | 10 | Implementation | Phase 2
54 | Workflow – Funding | Build funding automation | Workflow active | 8 | Implementation | Phase 2
55 | Assignment Rules | Configure assignment logic | Assignment active | 10 | Implementation | Phase 2
56 | Automation Testing | Test all workflows and automation | Tested automation | 10 | Implementation | Phase 2
57 | Form Build – Applications | Create forms | Forms ready | 12 | Implementation | Phase 2
58 | Form Logic | Configure conditional logic | Smart forms | 10 | Implementation | Phase 2
59 | Form Mapping | Map form to CRM | Data flow active | 8 | Implementation | Phase 2
60 | External Submission Setup | Configure external users | External flow ready | 8 | Implementation | Phase 2
61 | Document Handling Setup | Configure uploads and storage | Document system | 8 | Implementation | Phase 2
62 | Email Template Creation | Create templates | Templates ready | 10 | Implementation | Phase 2
63 | Notification Setup | Configure alerts | Notifications active | 8 | Implementation | Phase 2
64 | Consent Setup | Configure consent capture | Consent active | 6 | Implementation | Phase 2
65 | Security Review | Validate permissions | Security approved | 6 | Implementation | Phase 2
66 | Reporting – Applications | Build reports | Reports ready | 8 | Implementation | Phase 2
67 | Reporting – Assessments | Build reports | Reports ready | 8 | Implementation | Phase 2
68 | Reporting – Funding | Build reports | Reports ready | 8 | Implementation | Phase 2
69 | Dashboard Setup | Build dashboards | Dashboards ready | 10 | Implementation | Phase 2
70 | Integration Design | Finalise data flows | Design ready | 6 | Implementation | Phase 2
71 | Integration Build – Inbound | Configure inbound integrations | Integration live | 10 | Implementation | Phase 2
72 | Integration Build – Outbound | Configure outbound integrations | Integration live | 10 | Implementation | Phase 2
73 | Integration Error Handling | Configure failures | Error handling | 6 | Implementation | Phase 2
74 | Integration Testing | Test integrations | Tested integrations | 10 | Implementation | Phase 2
75 | QA Cycle – Phase 2 | Full QA | QA log | 14 | Implementation | Phase 2
76 | QA Fix Cycle – Phase 2 | Fix QA issues | Stable build | 12 | Implementation | Phase 2
77 | UAT Prep – Phase 2 | Prepare UAT | Scripts ready | 6 | Implementation | Phase 2
78 | UAT – Phase 2 | Execute UAT | Feedback | 12 | Implementation | Phase 2
79 | UAT Fix – Phase 2 | Apply fixes | Updated system | 10 | Implementation | Phase 2
80 | Sample Migration Prep | Prepare sample data | Ready data | 8 | Implementation | Phase 3
81 | Sample Migration | Import data | Data loaded | 8 | Implementation | Phase 3
82 | Migration Review | Validate data | Findings | 6 | Implementation | Phase 3
83 | Mapping Fix | Fix mapping | Updated mapping | 6 | Implementation | Phase 3
84 | Pilot Setup | Configure pilot | Pilot ready | 8 | Implementation | Phase 3
85 | Pilot Execution | Support pilot | Pilot active | 16 | Implementation | Phase 3
86 | Pilot Review | Collect feedback | Feedback log | 8 | Implementation | Phase 3
87 | Pilot Fix | Apply fixes | Updated system | 14 | Implementation | Phase 3
88 | QA – Phase 3 | QA cycle | QA results | 10 | Implementation | Phase 3
89 | QA Fix – Phase 3 | Fix QA | Stable system | 8 | Implementation | Phase 3
90 | UAT – Phase 3 | Validate pilot | UAT confirmation | 8 | Implementation | Phase 3
91 | UAT Fix – Phase 3 | Apply fixes | Updated system | 8 | Implementation | Phase 3
92 | Full Migration Prep | Prepare final data | Ready data | 10 | Implementation | Phase 4
93 | Full Migration | Import full dataset | Data live | 14 | Implementation | Phase 4
94 | Data Validation | Validate data | Clean data | 10 | Implementation | Phase 4
95 | Rollout Setup | Prepare rollout | Ready rollout | 8 | Implementation | Phase 4
96 | Rollout Execution | Deploy system | System live | 18 | Implementation | Phase 4
97 | Rollout Support | Support users | Stable usage | 16 | Implementation | Phase 4
98 | QA – Phase 4 | QA cycle | QA results | 8 | Implementation | Phase 4
99 | QA Fix – Phase 4 | Fix QA | Stable system | 8 | Implementation | Phase 4
100 | UAT – Phase 4 | Validate system | UAT sign-off | 10 | Implementation | Phase 4
101 | UAT Fix – Phase 4 | Apply fixes | Final system | 8 | Implementation | Phase 4
102 | Go-Live Prep | Final checks | Ready for launch | 4 | Implementation | Phase 5
103 | Go-Live | Deploy system | Live system | 6 | Implementation | Phase 5
104 | Hypercare | Support post go-live | Stable system | 12 | Implementation | Phase 5
105 | Training Prep | Prepare materials | Training ready | 8 | Implementation | Phase 4
106 | Training Delivery | Deliver sessions | Users trained | 10 | Implementation | Phase 4
107 | Project Management | Ongoing coordination | Managed project | 240 | Implementation | All Phases
1 | Training Plan | Define who needs training (admins, committees, assessors), what they need, and when (aligned to pilot and rollout) | Training plan | 4 | Training | Phase 3
2 | Session Structure Design | Define session breakdown (Applications, Assessment, Funding, Reporting, Admin) | Session structure | 4 | Training | Phase 3
3 | Training Data Setup | Prepare example records and scenarios for use in live sessions | Training data ready | 4 | Training | Phase 3
4 | Admin Training Delivery | Deliver live online session covering full system setup, management and control | Admins trained | 6 | Training | Phase 3
5 | Committee Training Delivery | Deliver sessions for application handling, decision making and day-to-day use | Committees trained | 8 | Training | Phase 3
6 | Assessor Training Delivery | Deliver sessions for scoring, reviewing and submitting feedback | Assessors trained | 6 | Training | Phase 3
7 | Training Recordings | Record sessions and provide access for reuse | Recordings available | 3 | Training | Phase 3
8 | Pilot Support Sessions | Run follow-up sessions during pilot to support users and answer questions | Users supported | 6 | Training | Phase 3
9 | Rollout Training Delivery | Deliver additional sessions for wider rollout users | Wider users trained | 10 | Training | Phase 4
10 | Additional Support Sessions | Provide drop-in or follow-up sessions post rollout | Questions resolved | 6 | Training | Phase 4
11 | Admin Deep Dive (Optional) | Additional focused session for admins post go-live if needed | Advanced admin support | 4 | Training | Phase 5
12 | Training Coordination | Schedule sessions, manage attendees, organise recordings | Training managed | 8 | Training | All Phases
1133
117