## Sheet1
# | Task Name | What Happens | Output | Hours | Stage | Phase
1 | Stakeholder & Planning Setup | Identify stakeholders, define session plan, confirm scope areas | Stakeholder map + plan | 4 | Requirements gathering/Process Mapping/Solution Output | Phase 1
2 | Application & Lifecycle Workshop | Full-day session covering application flow end-to-end (entry → submission → review → decision) including edge cases | Core lifecycle definition | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
3 | Assessment & Decision Workshop | Scoring models, assessor roles, moderation, approvals, exceptions | Assessment model | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
4 | Committee Variation Workshop | How different committees operate, key differences and constraints | Variation matrix | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
5 | Funding & Scholarship Workshop | Funding models, allocation, adjustments, lifecycle | Funding structure defined | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
6 | Data & Edge Case Workshop | Required data, dependencies, unusual scenarios, failures | Data requirements + edge cases | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
7 | Integration & Reporting Workshop | External systems, data flow, reporting needs (decision-led) | Integration + reporting definition | 7 | Requirements gathering/Process Mapping/Solution Output | Phase 1
8 | Engagement & Non-Application Workshop | Events, outreach, additional interactions | Engagement flows | 5 | Requirements gathering/Process Mapping/Solution Output | Phase 1
9 | Follow-up / Gap Session | Revisit unclear areas, challenge assumptions, close gaps | Gap log resolved | 5 | Requirements gathering/Process Mapping/Solution Output | Phase 1
10 | Process Mapping (Core) | Convert workshops into structured process maps (applications, assessment, funding) | Process maps v1 | 10 | Requirements gathering/Process Mapping/Solution Output | Phase 1
11 | Variation & Edge Case Mapping | Overlay variations and edge cases into core flows | Unified process model | 6 | Requirements gathering/Process Mapping/Solution Output | Phase 1
12 | Validation Session | Walkthrough with stakeholders, confirm accuracy, capture feedback | Feedback notes | 4 | Requirements gathering/Process Mapping/Solution Output | Phase 1
13 | Process Refinement | Apply feedback, finalise flows | Final process maps | 6 | Requirements gathering/Process Mapping/Solution Output | Phase 1
14 | System Translation | Convert processes into system design (entities, lifecycle, roles) | System design model | 8 | Requirements gathering/Process Mapping/Solution Output | Phase 1
15 | Data Definition | Define fields, ownership, validation rules | Data model + field list | 8 | Requirements gathering/Process Mapping/Solution Output | Phase 1
16 | Final Design Walkthrough | End-to-end review of system design | Final validation | 4 | Requirements gathering/Process Mapping/Solution Output | Phase 1
17 | Design Lock | Confirm sign-off and readiness for build | Approved design | 2 | Requirements gathering/Process Mapping/Solution Output | Phase 1
18 | Zoho Org Setup | Create org, configure company settings, branding, timezone, currency | Environment ready | 4 | Implementation | Phase 2
19 | Email & Domain Setup | Configure email routing, sender authentication, domain settings | Email working | 3 | Implementation | Phase 2
20 | App Enablement | Enable CRM, Forms, Analytics, Flow and required services | Apps active | 3 | Implementation | Phase 2
21 | Global Settings Review | Review and clean default system settings | Clean system base | 2 | Implementation | Phase 2
22 | Role Hierarchy Setup | Build hierarchy for central, committees, assessors | Role structure | 6 | Implementation | Phase 2
23 | Profile Setup | Configure module, field, action permissions | Profiles ready | 6 | Implementation | Phase 2
24 | Permission Rules | Configure sharing rules and visibility | Data access model | 8 | Implementation | Phase 2
25 | Initial User Creation | Create admin and key users | Users active | 4 | Implementation | Phase 2
26 | Module Creation – Individuals | Create core individual record structure | Module live | 4 | Implementation | Phase 2
27 | Module Creation – Applications | Create application structure | Module live | 4 | Implementation | Phase 2
28 | Module Creation – Committees | Create governance structure | Module live | 3 | Implementation | Phase 2
29 | Module Creation – Assessments | Create review structure | Module live | 4 | Implementation | Phase 2
30 | Module Creation – Funding | Create scholarship structure | Module live | 4 | Implementation | Phase 2
31 | Module Creation – Engagement | Create events/activity tracking | Module live | 5 | Implementation | Phase 2
32 | Module Creation – Organisations | Create partner/school structure | Module live | 5 | Implementation | Phase 2
33 | Field Creation – Individuals (Core) | Create demographic and contact fields | Fields live | 6 | Implementation | Phase 2
34 | Field Creation – Individuals (Extended) | Add lifecycle, status and classification fields | Fields live | 6 | Implementation | Phase 2
35 | Field Creation – Applications (Core) | Create application stage, type, source fields | Fields live | 7 | Implementation | Phase 2
36 | Field Creation – Applications (Decision) | Create decision and outcome fields | Fields live | 7 | Implementation | Phase 2
37 | Field Creation – Assessments | Create scoring and review fields | Fields live | 10 | Implementation | Phase 2
38 | Field Creation – Funding | Create funding allocation and tracking fields | Fields live | 10 | Implementation | Phase 2
39 | Field Creation – Committees | Create governance and membership fields | Fields live | 8 | Implementation | Phase 2
40 | Field Creation – Engagement | Create event/activity fields | Fields live | 8 | Implementation | Phase 2
41 | Lookup Relationships | Configure relationships between modules | Linked data | 12 | Implementation | Phase 2
42 | Related Lists Setup | Configure related record visibility | Navigation ready | 6 | Implementation | Phase 2
43 | Layout Build – Individuals | Build layouts and sections | Layout ready | 5 | Implementation | Phase 2
44 | Layout Build – Applications | Build layouts and sections | Layout ready | 6 | Implementation | Phase 2
45 | Layout Build – Assessments | Build layouts and sections | Layout ready | 4 | Implementation | Phase 2
46 | Layout Build – Funding | Build layouts and sections | Layout ready | 4 | Implementation | Phase 2
47 | Layout Build – Committees | Build layouts and sections | Layout ready | 4 | Implementation | Phase 2
48 | Validation Rules Setup | Configure required fields and rules | Validation active | 10 | Implementation | Phase 2
49 | Duplicate Rules Setup | Configure duplicate detection | Clean data rules | 6 | Implementation | Phase 2
50 | Lifecycle Stage Setup | Configure statuses and transitions | Lifecycle active | 10 | Implementation | Phase 2
51 | Workflow – Application | Build lifecycle automation | Workflow active | 14 | Implementation | Phase 2
52 | Workflow – Assessment | Build review automation | Workflow active | 10 | Implementation | Phase 2
53 | Workflow – Decision | Build decision automation | Workflow active | 10 | Implementation | Phase 2
54 | Workflow – Funding | Build funding automation | Workflow active | 8 | Implementation | Phase 2
55 | Assignment Rules | Configure assignment logic | Assignment active | 10 | Implementation | Phase 2
56 | Automation Testing | Test all workflows and automation | Tested automation | 10 | Implementation | Phase 2
57 | Form Build – Applications | Create forms | Forms ready | 12 | Implementation | Phase 2
58 | Form Logic | Configure conditional logic | Smart forms | 10 | Implementation | Phase 2
59 | Form Mapping | Map form to CRM | Data flow active | 8 | Implementation | Phase 2
60 | External Submission Setup | Configure external users | External flow ready | 8 | Implementation | Phase 2
61 | Document Handling Setup | Configure uploads and storage | Document system | 8 | Implementation | Phase 2
62 | Email Template Creation | Create templates | Templates ready | 10 | Implementation | Phase 2
63 | Notification Setup | Configure alerts | Notifications active | 8 | Implementation | Phase 2
64 | Consent Setup | Configure consent capture | Consent active | 6 | Implementation | Phase 2
65 | Security Review | Validate permissions | Security approved | 6 | Implementation | Phase 2
66 | Reporting – Applications | Build reports | Reports ready | 8 | Implementation | Phase 2
67 | Reporting – Assessments | Build reports | Reports ready | 8 | Implementation | Phase 2
68 | Reporting – Funding | Build reports | Reports ready | 8 | Implementation | Phase 2
69 | Dashboard Setup | Build dashboards | Dashboards ready | 10 | Implementation | Phase 2
70 | Integration Design | Finalise data flows | Design ready | 6 | Implementation | Phase 2
71 | Integration Build – Inbound | Configure inbound integrations | Integration live | 10 | Implementation | Phase 2
72 | Integration Build – Outbound | Configure outbound integrations | Integration live | 10 | Implementation | Phase 2
73 | Integration Error Handling | Configure failures | Error handling | 6 | Implementation | Phase 2
74 | Integration Testing | Test integrations | Tested integrations | 10 | Implementation | Phase 2
75 | QA Cycle – Phase 2 | Full QA | QA log | 14 | Implementation | Phase 2
76 | QA Fix Cycle – Phase 2 | Fix QA issues | Stable build | 12 | Implementation | Phase 2
77 | UAT Prep – Phase 2 | Prepare UAT | Scripts ready | 6 | Implementation | Phase 2
78 | UAT – Phase 2 | Execute UAT | Feedback | 12 | Implementation | Phase 2
79 | UAT Fix – Phase 2 | Apply fixes | Updated system | 10 | Implementation | Phase 2
80 | Sample Migration Prep | Prepare sample data | Ready data | 8 | Implementation | Phase 3
81 | Sample Migration | Import data | Data loaded | 8 | Implementation | Phase 3
82 | Migration Review | Validate data | Findings | 6 | Implementation | Phase 3
83 | Mapping Fix | Fix mapping | Updated mapping | 6 | Implementation | Phase 3
84 | Pilot Setup | Configure pilot | Pilot ready | 8 | Implementation | Phase 3
85 | Pilot Execution | Support pilot | Pilot active | 16 | Implementation | Phase 3
86 | Pilot Review | Collect feedback | Feedback log | 8 | Implementation | Phase 3
87 | Pilot Fix | Apply fixes | Updated system | 14 | Implementation | Phase 3
88 | QA – Phase 3 | QA cycle | QA results | 10 | Implementation | Phase 3
89 | QA Fix – Phase 3 | Fix QA | Stable system | 8 | Implementation | Phase 3
90 | UAT – Phase 3 | Validate pilot | UAT confirmation | 8 | Implementation | Phase 3
91 | UAT Fix – Phase 3 | Apply fixes | Updated system | 8 | Implementation | Phase 3
92 | Full Migration Prep | Prepare final data | Ready data | 10 | Implementation | Phase 4
93 | Full Migration | Import full dataset | Data live | 14 | Implementation | Phase 4
94 | Data Validation | Validate data | Clean data | 10 | Implementation | Phase 4
95 | Rollout Setup | Prepare rollout | Ready rollout | 8 | Implementation | Phase 4
96 | Rollout Execution | Deploy system | System live | 18 | Implementation | Phase 4
97 | Rollout Support | Support users | Stable usage | 16 | Implementation | Phase 4
98 | QA – Phase 4 | QA cycle | QA results | 8 | Implementation | Phase 4
99 | QA Fix – Phase 4 | Fix QA | Stable system | 8 | Implementation | Phase 4
100 | UAT – Phase 4 | Validate system | UAT sign-off | 10 | Implementation | Phase 4
101 | UAT Fix – Phase 4 | Apply fixes | Final system | 8 | Implementation | Phase 4
102 | Go-Live Prep | Final checks | Ready for launch | 4 | Implementation | Phase 5
103 | Go-Live | Deploy system | Live system | 6 | Implementation | Phase 5
104 | Hypercare | Support post go-live | Stable system | 12 | Implementation | Phase 5
105 | Training Prep | Prepare materials | Training ready | 8 | Implementation | Phase 4
106 | Training Delivery | Deliver sessions | Users trained | 10 | Implementation | Phase 4
107 | Project Management | Ongoing coordination | Managed project | 240 | Implementation | All Phases
1 | Training Plan | Define who needs training (admins, committees, assessors), what they need, and when (aligned to pilot and rollout) | Training plan | 4 | Training | Phase 3
2 | Session Structure Design | Define session breakdown (Applications, Assessment, Funding, Reporting, Admin) | Session structure | 4 | Training | Phase 3
3 | Training Data Setup | Prepare example records and scenarios for use in live sessions | Training data ready | 4 | Training | Phase 3
4 | Admin Training Delivery | Deliver live online session covering full system setup, management and control | Admins trained | 6 | Training | Phase 3
5 | Committee Training Delivery | Deliver sessions for application handling, decision making and day-to-day use | Committees trained | 8 | Training | Phase 3
6 | Assessor Training Delivery | Deliver sessions for scoring, reviewing and submitting feedback | Assessors trained | 6 | Training | Phase 3
7 | Training Recordings | Record sessions and provide access for reuse | Recordings available | 3 | Training | Phase 3
8 | Pilot Support Sessions | Run follow-up sessions during pilot to support users and answer questions | Users supported | 6 | Training | Phase 3
9 | Rollout Training Delivery | Deliver additional sessions for wider rollout users | Wider users trained | 10 | Training | Phase 4
10 | Additional Support Sessions | Provide drop-in or follow-up sessions post rollout | Questions resolved | 6 | Training | Phase 4
11 | Admin Deep Dive (Optional) | Additional focused session for admins post go-live if needed | Advanced admin support | 4 | Training | Phase 5
12 | Training Coordination | Schedule sessions, manage attendees, organise recordings | Training managed | 8 | Training | All Phases
1133
# | Task Name | What Actually Needs To Be Done | Output | Hours | Stage | Phase
1 | Portal Architecture Definition | Define full portal structure, user journeys (Applicant, Assessor, Committee), navigation and page hierarchy | Portal architecture | 12 | Implementation | Phase 2
2 | UX Wireframing | Create wireframes for all key pages (application, dashboards, review, decision screens) | Wireframes | 16 | Implementation | Phase 2
3 | UI Design Alignment | Apply branding, styling, responsive layout considerations | UI design ready | 10 | Implementation | Phase 2
4 | Front-End Environment Setup | Set up web framework, environments, repo, deployment pipeline | Dev environment ready | 12 | Implementation | Phase 2
5 | Authentication System Build | Build login, password reset, session handling, security flows | Secure authentication | 14 | Implementation | Phase 2
6 | User Role Framework (Frontend) | Build logic to differentiate Applicant, Assessor, Committee user experiences | Role-based UI | 14 | Implementation | Phase 2
7 | Portal Navigation Build | Create menus, routing, page transitions and navigation structure | Navigation working | 8 | Implementation | Phase 2
8 | Applicant Application Form UI | Build multi-step application interface with validation and UX flow | Application UI | 24 | Implementation | Phase 2
9 | Save & Resume Functionality | Enable saving progress and returning to incomplete applications | Save/resume working | 12 | Implementation | Phase 2
10 | Application Submission Logic | Validate and submit applications to backend | Submission working | 10 | Implementation | Phase 2
11 | Applicant Dashboard Build | Display application status, updates, required actions | Dashboard live | 16 | Implementation | Phase 2
12 | Applicant Document Upload UI | Build document upload and management interface | Document upload working | 10 | Implementation | Phase 2
13 | Assessor Dashboard Build | Display assigned applications and status | Dashboard live | 14 | Implementation | Phase 2
14 | Assessor Review Interface | Build scoring, commenting and review screens | Review UI | 18 | Implementation | Phase 2
15 | Assessor Save/Submit Logic | Handle partial saves and final submission of reviews | Review submission working | 10 | Implementation | Phase 2
16 | Committee Dashboard Build | Build overview of applications, metrics and statuses | Dashboard live | 14 | Implementation | Phase 2
17 | Committee Decision Interface | Build approve/reject logic and override capability | Decision UI | 16 | Implementation | Phase 2
18 | API Layer Setup | Build API endpoints to connect portal to Zoho CRM | API layer live | 20 | Implementation | Phase 2
19 | Data Sync – Create/Update | Handle creation and updates of records in CRM from portal | Data sync working | 18 | Implementation | Phase 2
20 | Data Sync – Read | Pull CRM data into portal views (applications, status, assignments) | Data display working | 16 | Implementation | Phase 2
21 | Error Handling Logic | Manage failed submissions, retries and validation errors | Stable handling | 10 | Implementation | Phase 2
22 | Security Hardening | Implement access control, session validation, input sanitisation | Secure portal | 10 | Implementation | Phase 2
23 | Portal QA – Internal | Test all user journeys across all roles | QA results | 16 | Implementation | Phase 2
24 | QA Fix Cycle | Resolve bugs identified during QA | Stable portal | 14 | Implementation | Phase 2
25 | UAT Scenario Preparation | Prepare real-world scenarios for user testing | UAT scripts | 6 | Implementation | Phase 2
26 | UAT Cycle (Pilot Users) | Users test portal functionality end-to-end | UAT feedback | 14 | Implementation | Phase 3
27 | UAT Fix Cycle | Apply changes based on UAT feedback | Updated portal | 12 | Implementation | Phase 3
28 | Pilot Portal Configuration | Configure portal users, permissions and data for pilot | Pilot ready | 8 | Implementation | Phase 3
29 | Pilot Support | Support users during pilot usage | Stable pilot | 12 | Implementation | Phase 3
30 | Pilot Feedback Review | Review usage, identify issues and improvements | Feedback log | 6 | Implementation | Phase 3
31 | Pilot Fix Cycle | Apply pilot improvements | Updated portal | 10 | Implementation | Phase 3
32 | QA – Post Pilot | Re-test portal after pilot changes | QA validation | 8 | Implementation | Phase 3
33 | UAT – Post Pilot | Confirm readiness for rollout | UAT sign-off | 8 | Implementation | Phase 3
34 | Rollout Portal Configuration | Configure portal for wider user base | Rollout ready | 8 | Implementation | Phase 4
35 | Rollout Execution | Deploy portal to all users | Portal live | 12 | Implementation | Phase 4
36 | Rollout Support | Support users accessing portal during rollout | Stable usage | 12 | Implementation | Phase 4
37 | QA – Post Rollout | Final QA across full user base | QA sign-off | 6 | Implementation | Phase 4
38 | UAT – Full Network | Validate portal across all user groups | UAT sign-off | 8 | Implementation | Phase 4
39 | Final Fix Cycle | Resolve final issues before go-live | Stable portal | 8 | Implementation | Phase 5
40 | Go-Live Deployment | Final release of portal to production | Portal live | 6 | Implementation | Phase 5
41 | Hypercare Support | Post go-live support and issue handling | Stable system | 10 | Implementation | Phase 5
488
1133
|  |  |  | 1621 | 189657