## Sheet1
Client Reported issue | Sam Comments | A2Z Actions | Client test working - SIGNED OFF. YES | client test not working - PLEASE PROVIDE FEEDBACK | Additional Comments Client | Additional Comments A2Z
The client will need to know and indicate to us whether the instruction they are putting on is a reinstruction. How can this be done? Our clients have specifically asked for this function.When a client is searching for an instruction, will it pick up any instructions they have made or that anyone in the client company has made? This would be necessary in order to link instructions and for them to know when a reinstruction is being made. | Completed | We’ve now implemented this functionality in both the CRM (Instruction module) and the Client Portal: A new field called “Instruction Category” has been added. This automatically stores whether the submitted instruction is a “New Instruction” or a “Re-instruction.” When a client submits an instruction, the system now checks the address (line 1, line 2, and postcode) against existing premises in the CRM. If a match is found, the instruction is automatically recognized as a re-instruction and linked to the existing premises record. If no match is found, a new premises record is created and marked as a new instruction. This means that whenever a client submits a form for a location that has already been instructed before, it will now be correctly flagged and categorised, ensuring both the client and the ID team can easily identify re-instructions and maintain a single, consolidated premises record in the system. Please feel free to test this on the portal - For example, create and submit a new Instruction record. Then again by submitting a new instruction for a previously used address. You’ll notice that it now links to the existing premises and is marked as a re-instruction accordingly. Sam to confirm all the amendments and finish deployment |  | Not working as of 19.11.25 in client portal. Put a new instruction through for a pub which has been in structed by me previously (twice). Nothing was picked up, recognised etc. There was no ability to mark this as a reinstruction. | What does 'added user' signify in the client instruction section of the client portal? We are unsure. Also it is beginning to look really messy. The premises name should always be first, now with the added columns it is getting pushed almost off the page. It would be better if the premises name was always in the first column and if this column was frozen so that when searching along the line, you still know what premises you are actually looking at. Currently not very user friendly. | Can you please let us know if we can close this one as completed?
SETTING UP REPORTS IN CRM Reports in CRM – none are set up and we do not know how to set any up. We need training on this or instruction documents on how to do it. Please remember that we have never used Zoho products before and it is vastly different to any other crm system we have used or are using. We need every user to open the system and have the ability to see what work they have to do. Either by sorting or via reports, but we do need something so that things are not missed. For example a report which we can run which will tell us what instructions are overdue for return from Investigators. |  | Certainly we can plan a training - in the meantime can you please refer to the link for your understanding on how reports can be created - https://help.zoho.com/portal/en/kb/crm/analytics-and-dashboards/reports/create-edit-reports/articles/understanding-and-building-reports#Creating_reports . If you would still require a training then please note this will be an additional cost for the hours of training. |  | We feel that having paid approx £40k for a brand new system, which none of us have any even basic knowledge of, that training would be part of the package A2Z offered. It's really poor from A2Z to then offer a link to follow, with the threat of addtional costs if more training is required. I am finding it difficult even working my way around this document never mind the new system. Please remember that none of us have any experience of anything Zoho. |  | Further training will require additional cost. Would you like to proceed? (estimate required)
COMPLETING MUSIC INSTRUCTIONS The completion of an instruction is causing some issues. We need the client portal, CRM and ID Portal saying the same thing. There is no clarity for either ID or the client. Currently, last stage for client portal is Audio tracks available (this should be Instruction Complete – once all the stages as described below have been completed). Currently last stage in CRM is Audio tracks available and next action – ‘send audio to client’ (even when this has been done and despite this not being the last action required, which is the invoice to be sent to client) This again needs to change to Instruction Complete and the next action would be blank. Last Stage in Portal is ‘ID Completed Site Visit’. This is fine, but would be better shown as ‘ID Completed Instructions’. 3.a INVOICING Melissa will have no idea what invoices have to be finalised for client without going into each instruction separately. We need a final stage or action (or both) so that Melissa can easily access what instructions are at the send invoice to client stage. Ideally after either any audio files are sent to client (or if the instruction is negative, after John sends the report), the stage/next action would indicate to Melissa that the invoice is now ready to be sent to client (we cannot send the invoice before any audio files are sent). Also it may be better if in the report, the tick boxes for audio files sent and invoice sent are put in that order. 3.b STAGES For your information – the flow is as follows: Jackie completes initial review – music tracks become available to client (if positive result) John completes final review – saves and uploads report which becomes available to client If positive result (music found), John presses tickbox to alert Gregory/Mat to sent audio files to client (they will get email, however it would be easier if they could sort or report on jobs are needing done on system) John completes initial invoice review Gregory/Mat send link to audio files to client Melissa or Alison complete final invoice review (cannot do this until report and any audio files are sent to client – how will she know when this is complete. An email is no use, would be easier if a report or sorting could be completed on system, so that she can go through each one as required) Instruction is marked as complete. | Everything working fine. | Sam to test and check this is working- All the requested changes have now been implemented as per your specifications. 1. Final Stage Alignment The final stage across all three systems (Client Portal, CRM, and ID Portal) is now “Instruction Complete.” This ensures full consistency — once all tasks (reviews, audio delivery, and invoicing) are completed, the instruction is marked as complete in every system simultaneously. 2. Stage Updates Client Portal: The last stage has been updated from “Audio Tracks Available” to “Instruction Complete.” CRM: The final stage is now “Instruction Complete.” The “Next Action” field is cleared automatically when this stage is reached. Next action – ‘send audio to client’ -> this indicates the Open Activity(Task) in the Instruction and which is not marked as completed. When Audio Files is marked as checked in the portal and report submitted, a task gets generated in Instruction which was already explained earlier. The respective team member has to review the task and close the task following the process without fail. If an user does not mark the task complete then the system shows next action – ‘send audio to client’. ID Portal: The previous stage “ID Completed Site Visit” now displays as “ID Completed Instructions” for clarity. 3. Invoicing Flow Enhancements A new final stage/action indicator has been added to identify when an instruction is ready for invoicing. Once either: Audio files are sent to the client (for positive results), or The report is submitted (for negative results), the system now automatically updates the status so Melissa (or Alison) can easily filter or report on all instructions that are ready for invoicing — without having to open each one individually. Ideally after either any audio files are sent to client (or if the instruction is negative, after John sends the report), the report moves to AWAITING INVOICE under Reort in Progress and also Invoice moves to INVOICE AWAITING FINAL REVIEW under Invoice Review. Melissa should refer to Report in Progress -> AWAITING INVOICE for reports. And for Invoices, Go to Invoice Review -> INVOICE AWAITING FINAL REVIEW The order of completion checkboxes in reports has been updated. 4. Instruction Completion Workflow The process now follows this consistent and logical flow: Jackie completes initial review – music tracks become available (if positive). John completes final review and uploads report. John flags when audio files are ready to send (triggers Gregory/Mat notification). Gregory/Mat send audio links to client. Melissa/Alison complete invoice review once all deliverables are sent. Instruction automatically updates to Instruction Complete across all systems. |  |  |  | Has this been tested ?
MISCELLANEOUS EXPENSES IN INVOICE. - This is what you have already mentioned but we have some follow up questions for this We need the facility for the Investigators to upload their expenses, e.g. parking receipts, entry fees, food and drink receipts. I understand that this would involve more work, however could we perhaps either create another upload category as Miscellaneous or change the Sketch Plan one to this, to incorporate everything? |  | As you mentioned, this is an additional work, it will have to be considered as a change request. We need some clarity before we estimate the effort. Here are my questions. At the moment we already have a category in the Invoice form, where the Investigator can add in their expenses there and also add the description, say Food, Parking etc., Can this only be considered as Miscellaneous? Do you want us to add an one more option under Category say Miscellaneous, and allow investigators to add their miscellaneous expenses there? Do we just want the investigators to be able to upload when they're doing the invoice, where should these evidence be stored? Also, what needs to happen after? we already know the answers to above 3 questions however we need to know what needs be done after uploading the receipts where do you need to store these for example in the Workdrive or just leave them in the portal? |  |  |  | change request, would you like to proceed?Estimate required
ASSIGNMENT MAP. COMPLETED INSTRUCTIONS ARE NOT BEING REMOVED FORM SYSTEM?? We have noticed that on the assignment map, when the Investigator completes his report and returns it to us, it is still showing as being assigned on the map. If these are not removed, very quickly it will become unmanageable and we will not be able to see anything. In the Investigator portal, the live assignments disappear as required when the report is completed. The only pins on the map, should be as follows: Investigators location Instructions ready for allocation Instructions allocated | Tested | These has been implemented. Sam to test and fix if any issues |  |  |  | Can you please let us know if we can close this one as completed?
SNIPPING AND PASTING VISUALS INTO REPORTS In Zoho Writer, there is no option to add cut and pasted snips. John will have the audio/visual footage open on another screen when he is completing the report and will take a snip of each necessary photo required, e.g. speakers on the wall, advertising outside, who is in charge. He does this at present by using the MS snipping tool and then pastes it into the Word Document report. We cannot work out how he will do this using Zoho Writer. It is not an option to save every snip and then import it, as it would take far too much time. Can you advise please? We can see that there is an | Video has all required information. | Sharing the video. Please see if that helps. Refer to the video link below. https://documents.a2zcloud.com/external/04fbc1a3969af656aff66b180f9e1aee419dba0cae0be4965813c892db67a501 Password: A2Z123. Sam to check if this video is accurate and it as per clients request |  |  |  | Can you please let us know if we can close this one as completed?
INVOICE In regards to the invoice, each line is too large and it is making the invoice go on to be 2 pages. Can this be changed so that the spacing is only what is required, so that the invoice only ever is one page long? I didn’t check during the tests, but can you remove any notes that the Investigator puts on, for example in Pot Still, against the mileage? We would not necessarily want their notes on the final invoice. | Fixed. | The following updates have now been made: Layout: Line spacing has been reduced so the invoice now fits neatly on a single page. Notes: Investigator notes/description (e.g., against mileage) are no longer shown on the client invoice. Sam to check |  |  |  | Can you please let us know if we can close this one as completed?
8. CLIENT SEARCH FOR PREMISES | Completed. | Sam to fix |  |  |  | I will get back to you on this next week
ADDRESS LOCATOR IN CRM This is working well, however although the mapping co-ordinates show, the actual address locator field stays blank, after we have confirmed the location. It just looks a bit strange, we think it would be better if something would appear in that field telling us that we have confirmed the address for the purposes of the assignment map in the portal. | Working. | As part of the recent update, the Address Locator field in the Premises module is no longer required — it isn’t linked to any workflow or used in the mapping process. The assignment map in the portal now functions fully based on the confirmed coordinates alone. To keep the interface clean and avoid confusion, the Address Locator field has therefore been removed. Sam to check this is working |  |  |  | Can you please let us know if we can close this one as completed?
EMAIL TO CLIENT IF DPS OR LICENCEE DETAILS DIFFER – DISAPPEARING FROM SYSTEM We have noted that when an email is sent to the client as above, when the client replies to us (we are using the notes section to mark what they say), and we thereafter move the stages on, this email disappears from the system. We would prefer if all emails are kept in the system, for accuracy purposes | Not able to replicate | Tried to replicate the issue reported but could not replicate. Followed the same scenario as mentioned but I could not replicate. Could you please elaborate and help us understand this issue? Sam to test to see if you can replicate it |  |  |  | Does the issue still persists ? We need examples so that we can test it please if no longer occurs then can we close this?
CAN AND HOW DO WE IMPORT EMAILS INTO THE SYSTEM ( We will need this for continuity, if the client replies to any email sent to them regarding a premises. |  | Yes, emails can be automatically captured in Zoho CRM through the built-in email integration feature. This ensures full continuity when clients reply to any email sent from the CRM. Please refer and follow the steps mentioned here to do the Email configuration in all your team members account. It's needed to be done by the users. Maybe check with Hydin if this is set up |  |  |  | Do you still need further assistance on this?
NAMING FORMATS FOR REPORTS AND INVOICES Can this be changed from having dashes in between, it just makes it look messy. Also I noticed that with the invoice, the dashes turn to underscores. Again, this just looks messy. | Working. | The naming has now been updated — dashes and underscores have been removed for a cleaner, more consistent appearance. Sam to check |  |  |  | Do you still need further assistance on this? Or can it be closed?
Premises: Records are being duplicated, and when entering a name or postcode, the system isn’t recognising that it already exists. | Fixed. | To be worked on with Buket - sam to confirm |  |  |  | I will get back to you on this next week